## Master Task List
RATION VEDA — Digital Setup Master Task List
Complete checklist for Social Media, Email, Website & App setup
# | Task | Sub-Tasks / Exact Steps | Tools / Platform | Owner / Who Does It | Priority | Timeline | Status
1. EMAIL & DOMAIN SETUP (DO FIRST — Everything else depends on this)
1A. Domain & Hosting
1 | Verify domain ownership for rationveda.com | 1. Login to your domain registrar (GoDaddy/Namecheap/Google Domains) 2. Confirm rationveda.com is registered and active 3. Check expiry date — renew if expiring within 6 months 4. Enable auto-renewal and domain lock 5. Save registrar login credentials securely (use a password manager like 1Password or Bitwarden) | GoDaddy / Namecheap / Google Domains | Founder | P0 - Critical | Day 1 | Not Started
2 | Set up DNS management | 1. Go to domain registrar → DNS Settings 2. Note down current nameservers 3. If using Cloudflare (recommended): create free account → Add site → Update nameservers at registrar to Cloudflare’s 4. Cloudflare gives free SSL, CDN, and DDoS protection 5. Save Cloudflare login: email + password + 2FA | Cloudflare (free) or registrar DNS | Founder / Dev | P0 - Critical | Day 1 | Not Started
1B. Professional Email Setup
3 | Choose email provider & create workspace | Option A (Recommended): Google Workspace — ₹136/user/month • Go to workspace.google.com → Get Started • Enter business name: Ration Veda • Domain: rationveda.com • Create admin account: nishtha@rationveda.com • Complete payment (monthly or annual) Option B: Zoho Mail — Free for up to 5 users • Go to zoho.com/mail → Business Email • Follow setup wizard | Google Workspace / Zoho Mail | Founder | P0 - Critical | Day 1-2 | Not Started
4 | Verify domain with email provider | 1. Provider gives you a TXT record (e.g., google-site-verification=xxxxx) 2. Go to Cloudflare/registrar DNS → Add TXT record 3. Host: @ ¦ Value: verification string 4. Wait 5-30 mins for propagation 5. Click Verify in provider dashboard | DNS panel + Email provider | Founder / Dev | P0 - Critical | Day 2 | Not Started
5 | Set up MX records for email delivery | Google Workspace MX Records (add ALL 5): • Priority 1: ASPMX.L.GOOGLE.COM • Priority 5: ALT1.ASPMX.L.GOOGLE.COM • Priority 5: ALT2.ASPMX.L.GOOGLE.COM • Priority 10: ALT3.ASPMX.L.GOOGLE.COM • Priority 10: ALT4.ASPMX.L.GOOGLE.COM Delete any existing MX records first | Cloudflare / DNS panel | Dev | P0 - Critical | Day 2 | Not Started
6 | Set up SPF, DKIM & DMARC (anti-spam) | SPF: Add TXT record → Host: @ ¦ Value: v=spf1 include:_spf.google.com ~all DKIM: Google Admin → Apps → Google Workspace → Gmail → Authenticate Email → Generate DKIM → Add TXT record DMARC: Add TXT record → Host: _dmarc ¦ Value: v=DMARC1; p=quarantine; rua=mailto:dmarc@rationveda.com | Google Admin + DNS panel | Dev | P0 - Critical | Day 2 | Not Started
7 | Create all required email addresses | Create these accounts in Google Admin → Users: • nishtha@rationveda.com (Admin / Founder) • contact@rationveda.com (General inquiries) • orders@rationveda.com (Order management) • support@rationveda.com (Customer support) • marketing@rationveda.com (Social media, collabs) • info@rationveda.com (Alias → forward to contact@) Set strong passwords (12+ chars, mixed case, numbers, symbols) Enable 2FA on ALL accounts | Google Workspace Admin | Founder | P0 - Critical | Day 2-3 | Not Started
8 | Set up email signatures for all accounts | Use consistent brand signature: • Name + Designation • Ration Veda logo (small) • Phone number • Website: www.rationveda.com • Instagram handle • Tagline: “Hand-pounded. Region-sourced. Unmatchable.” Use tool like WiseStamp or HubSpot Email Signature Generator (free) | Gmail Settings / WiseStamp | Marketing | P1 - High | Day 3 | Not Started
2. SOCIAL MEDIA SETUP
2A. Instagram (PRIMARY platform — setup first)
9 | Create/convert to Instagram Business Account | 1. If existing personal account: Settings → Account → Switch to Professional Account → Business 2. If new: Download Instagram → Sign up with marketing@rationveda.com 3. Username: @rationveda (or @ration.veda if taken) 4. Category: Food & Beverage Company 5. Connect to Facebook Business Page (creates one if needed) 6. Save credentials in password manager | Instagram app + Facebook | Founder | P0 - Critical | Day 3 | Not Started
10 | Complete Instagram profile optimization | Profile Photo: Ration Veda logo (clean, visible at small size) Name field: Ration Veda ¦ Hand-Pounded Spices Bio (150 chars max): “Hand-pounded spices ✧ Imam-Dasta crafted Region-sourced from India’s finest farms Guntur • Rajasthan • Maharashtra • Punjab → Order via link below” Link: Use Linktree (free) → add WhatsApp order link, website, YouTube Action Button: Add WhatsApp button (Settings → Business → Action Buttons) | Instagram + Linktree | Marketing | P0 - Critical | Day 3 | Not Started
11 | Create Instagram Highlights structure | Create these Highlight covers (use Canva): • Our Process — Imam-Dasta videos, hand-pounding • Products — Each spice with details • Reviews — Customer testimonials • Gifting — Gift box options • Sourcing — Farm/origin stories • How to Order — Step-by-step • Events — Market/event clips Design covers in Ration Veda brand colors (earthy green/brown) | Canva (free) + Instagram | Marketing | P1 - High | Day 4-5 | Not Started
12 | Set up Instagram Shopping (future-ready) | 1. Ensure Facebook Business Page is connected 2. Go to Commerce Manager (business.facebook.com/commerce) 3. Create a catalog → E-commerce → Upload products manually 4. Add all products: name, description, price, images 5. Submit for Instagram Shopping review (takes 1-7 days) 6. Once approved: tag products in posts and stories | Meta Commerce Manager | Marketing / Dev | P2 - Medium | Week 2 | Not Started
13 | Plan first 30 days of Instagram content | Week 1: Brand intro (process, story, founder’s why) Week 2: Product spotlights (one spice per day with recipe) Week 3: Behind-the-scenes (sourcing trips, hand-pounding) Week 4: Social proof (customer reactions, events, testimonials) Content mix: 4-5 Reels/week + 2 carousel posts + daily Stories Post times: 11am-1pm and 6pm-8pm IST Use hashtags: #HandPoundedSpices #RationVeda #ImamDasta #AuthenticSpices #PureSpices #IndianSpices #FarmToKitchen | Instagram + Canva + CapCut (for Reels editing) | Marketing | P1 - High | Week 1-4 | Not Started
2B. YouTube
14 | Create YouTube Brand Channel | 1. Go to youtube.com → Sign in with marketing@rationveda.com 2. Click profile → Create Channel → Use custom name: Ration Veda 3. Channel Settings: • Handle: @RationVeda • Description: “Ration Veda brings back India’s ancient hand-pounding (Imam-Dasta) technique to create spices that are unmatchable in taste, authenticity and purity. From Guntur chillies to Rajasthani coriander — we source from the best and craft with tradition.” • Links: Website, Instagram, WhatsApp • Banner: Use Canva YouTube banner template (2560x1440px) • Profile pic: Ration Veda logo 4. Verify channel for custom URL | YouTube + Google Account | Marketing | P1 - High | Day 4 | Not Started
15 | Plan YouTube content pillars | Content pillars: • Process Videos: Hand-pounding sessions, Imam-Dasta in action (most viral potential) • Sourcing Journeys: Travel to Guntur farms, Rajasthan, Maharashtra — show the origin • Recipe Series: “Cook with Ration Veda” — simple recipes using your spices • Knowledge Series: “Spice Science” — why hand-pounding preserves oils, heat damage explained • Customer Stories: Real families tasting the difference Start with: 2 videos/month (Shorts can be repurposed from Instagram Reels) Equipment needed: Smartphone + tripod + basic ring light + lapel mic (₹2000-3000 total) | YouTube + editing software (CapCut/DaVinci Resolve free) | Marketing | P1 - High | Week 2+ | Not Started
2C. Facebook
16 | Set up Facebook Business Page | 1. Already auto-created when connecting Instagram Business 2. Go to facebook.com/pages/create if not 3. Page name: Ration Veda 4. Category: Food & Beverage Company, Spice Store 5. Add all details: address, phone, website, hours 6. Upload cover photo (Canva — 820x312px) and profile photo 7. Add CTA button: “Send WhatsApp Message” 8. Create Facebook Shop (links to same Commerce Manager catalog) 9. Invite friends/family to like the page for initial base | Facebook | Marketing | P1 - High | Day 3-4 | Not Started
2D. LinkedIn
17 | Create LinkedIn Company Page | 1. Go to linkedin.com → Work → Create a Company Page 2. Company name: Ration Veda 3. LinkedIn URL: linkedin.com/company/rationveda 4. Industry: Food & Beverages 5. Company size: 2-10 employees 6. Logo + cover image (Canva — 1128x191px) 7. About section: Brand story focused on B2B angle — partnerships, corporate gifting, retail expansion 8. Use for: Corporate gifting outreach, hiring, investor visibility, B2B partnerships | LinkedIn | Founder | P2 - Medium | Week 2 | Not Started
2E. WhatsApp Business
18 | Upgrade to WhatsApp Business API (if not done) | You’re already using Interakt. Ensure: 1. Business profile is complete: name, description, address, email, website 2. Catalog is updated with ALL products (including new SKUs as they launch) 3. Quick replies set up: “Hi! Thanks for reaching out to Ration Veda...” 4. Auto-greeting message for new chats 5. Away message for off-hours 6. Labels: New Order, Processing, Shipped, Repeat Customer, Corporate Inquiry 7. Create broadcast lists: All Customers, Gurgaon, Delhi, Corporate, Events | WhatsApp Business / Interakt | Operations | P0 - Critical | Day 1-2 | Not Started
2F. Other Platforms
19 | Create Google Business Profile | 1. Go to business.google.com 2. Business name: Ration Veda 3. Category: Spice Store, Food Products Supplier 4. Add address (warehouse), phone, website, hours 5. Upload 10-15 high-quality product photos 6. Ask 20+ existing customers to leave Google reviews 7. This helps in local search: “premium spices near me” | Google Business Profile | Marketing | P1 - High | Day 5 | Not Started
20 | Register on X (Twitter) | 1. Sign up at x.com with marketing@rationveda.com 2. Handle: @RationVeda 3. Bio: Short brand description + link 4. Low priority for now — use to reshare Instagram content and engage with food community 5. Follow food bloggers, health influencers, spice-related accounts | X (Twitter) | Marketing | P3 - Low | Week 3 | Not Started
21 | Create Pinterest Business Account | 1. Go to business.pinterest.com → Sign up 2. Business name: Ration Veda 3. Create boards: Indian Spices, Recipes, Kitchen Essentials, Gift Ideas, Health & Wellness 4. Pin product photos with links to website/WhatsApp 5. Pinterest drives long-tail traffic — good for recipe content | Pinterest | Marketing | P3 - Low | Week 3 | Not Started
3. WEBSITE — www.rationveda.com
3A. Platform Selection & Setup
22 | Choose website platform | Recommended: Shopify (₹2,000/month Basic plan) • Built for e-commerce, easy to manage, great themes • Handles payments, inventory, shipping • WhatsApp integration plugins available Alternative: WordPress + WooCommerce (cheaper but needs more maintenance) For NOW (Phase 1): Even a simple Shopify site with “Order via WhatsApp” button works perfectly. Don’t over-invest in website until Q-comm and D2C scale. | Shopify / WordPress | Dev / Founder | P0 - Critical | Day 5-7 | Not Started
23 | Purchase Shopify plan & connect domain | 1. Go to shopify.com → Start free trial (3 days free, then ₹2,000/month) 2. Store name: Ration Veda 3. Connect domain: • Shopify Settings → Domains → Connect existing domain • Enter rationveda.com • Add CNAME record in Cloudflare: shops.myshopify.com • Add A record: 23.227.38.65 4. Enable SSL (automatic with Shopify) 5. Save Shopify admin credentials securely | Shopify + Cloudflare DNS | Dev | P0 - Critical | Day 5-6 | Not Started
3B. Website Design & Content
24 | Select and customize Shopify theme | Recommended free themes: Dawn, Craft, Taste Customize: • Colors: Brand green (#1B4332), earthy brown, cream background • Fonts: Clean serif for headings, sans-serif for body • Logo in header • Favicon (small logo icon) Keep it clean, premium, minimal — let the products speak | Shopify Theme Editor | Dev / Designer | P1 - High | Day 6-8 | Not Started
25 | Create all website pages with content | Pages to create: 1. HOME: Hero banner (lifestyle shot + tagline) → “Hand-Pounded. Region-Sourced. Unmatchable.” ¦ Featured products ¦ Process section ¦ Testimonials ¦ CTA: Order on WhatsApp 2. ABOUT US / OUR STORY: Founder story, why Ration Veda exists, Imam-Dasta explanation with video, sourcing philosophy, team photo 3. OUR PROCESS: Detailed visual walkthrough — sourcing → cleaning → hand-pounding → packaging. Photos/videos at each step 4. PRODUCTS (Collection page): All products with photos, descriptions, weight, price. Each product page: origin story, taste notes, suggested use, ingredients, nutrition 5. GIFTING: Gift box options, corporate gifting inquiry form, customize options 6. CONTACT US: Form (name, email, phone, message), WhatsApp button, email: contact@rationveda.com, address 7. FAQ: Shipping, returns, shelf life, how is this different from other brands, are you organic, payment methods 8. BLOG (future): Recipes, spice education, sourcing stories | Shopify + Canva for images | Content Writer + Dev | P0 - Critical | Day 7-14 | Not Started
26 | Add all products to Shopify catalog | For each product add: • Product title (e.g., “Guntur Chilli Powder — Hand-Pounded”) • Description: Origin, process, taste profile, usage suggestions • Price + Compare-at price (if showing discount) • SKU code • Weight and dimensions • 4-6 high-quality photos (product, packaging, in-use, close-up) • Variants: 50g, 100g, 250g (when available) • Tags for filtering: chilli, coriander, turmeric, garam masala, etc. • SEO title and meta description for each product | Shopify Admin → Products | Marketing + Dev | P0 - Critical | Day 8-12 | Not Started
27 | Set up WhatsApp order redirect | Since direct checkout isn’t priority yet: 1. Install Shopify app: “WhatsApp Chat + Cart Recovery” (free options: SuperLemon, WhatsApp Chat by Suspended) 2. Configure: • WhatsApp number: your business number • Pre-filled message: “Hi Ration Veda! I’d like to order: [product details]” 3. Replace “Add to Cart” button text with “Order via WhatsApp” 4. Add floating WhatsApp button on all pages 5. Also add WhatsApp link in footer and Contact page | Shopify App Store | Dev | P0 - Critical | Day 10-12 | Not Started
3C. Website Technical Setup
28 | Set up Google Analytics & Search Console | Google Analytics 4: 1. Go to analytics.google.com → Create account → Ration Veda 2. Create property → Web → Enter rationveda.com 3. Get Measurement ID (G-XXXXXXX) 4. Add to Shopify: Online Store → Preferences → Google Analytics Google Search Console: 1. Go to search.google.com/search-console 2. Add property → Domain → rationveda.com 3. Verify via DNS TXT record in Cloudflare 4. Submit sitemap: rationveda.com/sitemap.xml | Google Analytics + Search Console | Dev | P1 - High | Day 12-13 | Not Started
29 | Set up Meta Pixel & tracking | 1. Go to Facebook Events Manager (business.facebook.com/events_manager) 2. Create Pixel → Name: Ration Veda Pixel 3. Get Pixel ID 4. Add to Shopify: Settings → Online Store → Preferences → Facebook Pixel 5. Verify with Facebook Pixel Helper Chrome extension 6. This enables retargeting ads and lookalike audiences later | Meta Business Suite + Shopify | Dev / Marketing | P1 - High | Day 12-13 | Not Started
30 | Basic SEO setup | 1. Set homepage title: “Ration Veda — Hand-Pounded Premium Spices ¦ Region-Sourced from India” 2. Meta description: “Discover authentic hand-pounded spices crafted using the ancient Imam-Dasta technique. Guntur chilli, Rajasthani coriander, Rajapuri turmeric & more. Pure. Unmatchable.” 3. Add alt text to ALL images 4. Create URL structure: rationveda.com/products/guntur-chilli-powder 5. Add schema markup (Shopify apps: JSON-LD for SEO) 6. Submit sitemap to Google Search Console | Shopify + Google Search Console | Dev | P1 - High | Day 13-14 | Not Started
31 | Set up essential Shopify apps | Install these free/low-cost apps: • WhatsApp Chat plugin (for order redirect) • SEO app (JSON-LD for SEO or SEO Manager) • Privy or Mailchimp (email popup for list building) • Loox or Judge.me (product reviews) • Google channel (for Google Shopping listing) • Facebook & Instagram channel (for social commerce) • Shipping calculator (if enabling direct orders later) | Shopify App Store | Dev | P2 - Medium | Week 2-3 | Not Started
4. MOBILE APP
4A. App Strategy Decision
32 | Decide: Build app now or later? | RECOMMENDATION: DO NOT build a native app now. Here’s why: • You have < 1000 customers — app downloads will be very low • Cost: ₹3-8 lakhs for basic app, ongoing maintenance • Better ROI: Invest that money in products, events, marketing INSTEAD DO THIS: 1. Make your Shopify website mobile-optimized (it is by default) 2. Add “Add to Home Screen” prompt (PWA — Progressive Web App) 3. Use WhatsApp Business catalog as your “app” for now 4. Build a proper app at 5,000+ active customers | Strategic Decision | Founder | P0 - Critical | Day 1 (decide) | Not Started
4B. If Building App Later (at 5000+ customers)
33 | Choose app development approach | Option 1: Shopify Mobile App Builder (₹5,000-15,000/month) • Apps like Shopney, Vajro, or Tapcart • Converts your Shopify store into a mobile app • No coding needed, syncs automatically • Push notifications, in-app purchases Option 2: Custom App (React Native / Flutter) — ₹4-8 lakhs • Full control, custom features • Needs developer team or agency • Only worth it at serious scale (10,000+ users) Option 3: Progressive Web App (PWA) — ₹50,000-1 lakh • Works like an app from the browser • No app store listing needed • Good middle ground | Shopney / Vajro / Custom Dev | Dev / Agency | P3 - Later | Month 6-9 | Not Started
4C. Immediate App-Like Experience (Do Now)
34 | Set up WhatsApp catalog as mini-app | 1. Open WhatsApp Business → Business Tools → Catalog 2. Add ALL products with: • High-quality product photo • Name, price, description • Product link (to website) 3. Organize by collections if available 4. Share catalog link: wa.me/c/91XXXXXXXXXX 5. Add this link to Linktree, Instagram bio, website | WhatsApp Business | Marketing | P0 - Critical | Day 3-4 | Not Started
35 | Enable PWA on Shopify website | 1. Install Shopify app: “PWA & AMP” or “Progressify” 2. Configure: App icon (Ration Veda logo), splash screen, theme color 3. When customers visit website on mobile, they’ll get prompted: “Add Ration Veda to Home Screen” 4. This creates an app-like icon on their phone 5. Opens website in full-screen mode (looks like an app) 6. Loads faster on repeat visits | Shopify PWA App | Dev | P1 - High | Week 2 | Not Started
5. CREDENTIALS & SECURITY MASTER LIST
36 | Set up a password manager | 1. Create a 1Password Teams account (₹300/user/month) OR use Bitwarden (free) 2. Create a vault: “Ration Veda Business” 3. Store ALL credentials here (never in notes/WhatsApp/email) 4. Enable 2FA on the password manager itself 5. Share vault access with team members as needed | 1Password / Bitwarden | Founder | P0 - Critical | Day 1 | Not Started
37 | Create and store all credentials | Store these in password manager: • Domain registrar: URL, email, password, 2FA • Cloudflare: email, password, 2FA • Google Workspace Admin: email, password, 2FA, recovery email • Each email account: address, password • Shopify: email, password, 2FA • Instagram: email/phone, password, 2FA • Facebook Page: linked personal account • YouTube: Google account credentials • LinkedIn: email, password • WhatsApp Business / Interakt: phone, login • Google Analytics: Google account • Meta Business Suite: Facebook login • Canva: email, password • Linktree: email, password | 1Password / Bitwarden | Founder | P0 - Critical | Ongoing | Not Started
38 | Enable 2FA on all critical accounts | MUST enable 2-Factor Authentication on: • Domain registrar (most critical — controls everything) • Google Workspace Admin • Shopify • Instagram (Settings → Security → Two-Factor Authentication) • Facebook • Meta Business Suite • Password manager Use authenticator app (Google Authenticator or Authy), NOT SMS | Google Authenticator / Authy | Founder | P0 - Critical | Day 2-3 | Not Started
6. CONTENT & CREATIVE ASSETS NEEDED
39 | Product photography session | Hire a food photographer OR DIY with good phone: • Individual product shots (white background) • Lifestyle shots (spices in kitchen, cooking scenes) • Packaging close-ups (potli texture, labels) • Process shots (Imam-Dasta in action) • Gift box photography • Raw material shots (whole chillies, coriander seeds, turmeric roots) • Flat-lay compositions Need: 15-20 photos per product, 30-40 lifestyle/brand photos Budget: ₹5,000-15,000 for professional shoot | Photographer / Smartphone + lightbox | Marketing + Photographer | P0 - Critical | Day 4-7 | Not Started
40 | Create brand design assets in Canva | Create these in Canva (use Brand Kit for consistency): • Logo variations: full color, white, black, icon-only • Instagram post templates (3-4 templates) • Instagram Story templates (3-4 templates) • YouTube banner and thumbnail templates • Facebook cover photo • LinkedIn cover photo • Email signature banner • WhatsApp catalog images template • Business card design • Letterhead • Invoice template Save all as a Canva Brand Kit with colors, fonts, logos | Canva Pro (₹3,500/year) | Designer / Marketing | P1 - High | Day 5-10 | Not Started
41 | Write brand copy document | Create a master copy document with: • Brand taglines (3-5 options for different contexts) • Elevator pitch (30 seconds) • Full brand story (500 words) • Product descriptions for all 4 current products • FAQ answers (10-15 common questions) • Email templates: welcome, order confirmation, shipping update, review request • WhatsApp message templates: greeting, order process, follow-up • Social media bio text for all platforms • SEO keywords list | Google Docs / Notion | Founder + Copywriter | P1 - High | Day 5-10 | Not Started

## Credentials Tracker
RATION VEDA — Credentials & Access Tracker
⚠️ DO NOT share this sheet. Store passwords in 1Password/Bitwarden, not here. Use "Password Hint" column only.
Platform | URL | Email / Username | Password Hint | 2FA Enabled? | Recovery Email | Notes
Domain & Hosting
Domain Registrar | godaddy.com / namecheap.com |  | Set in 1Password | YES ✔ | personal email | Most critical — controls everything
Cloudflare | dash.cloudflare.com |  | Set in 1Password | YES ✔ | nishtha@rationveda.com | DNS, SSL, CDN
Email
Google Workspace Admin | admin.google.com | nishtha@rationveda.com | Set in 1Password | YES ✔ | personal Gmail | Controls all email accounts
contact@rationveda.com | mail.google.com | contact@rationveda.com | Set in 1Password | YES ✔ |  | General inquiries
orders@rationveda.com | mail.google.com | orders@rationveda.com | Set in 1Password | Optional |  | Order management
support@rationveda.com | mail.google.com | support@rationveda.com | Set in 1Password | Optional |  | Customer support
marketing@rationveda.com | mail.google.com | marketing@rationveda.com | Set in 1Password | YES ✔ |  | Social accounts use this
Social Media
Instagram | instagram.com | @rationveda | Set in 1Password | YES ✔ | marketing@rationveda.com | Business account
Facebook Page | facebook.com/rationveda | Linked to personal FB | N/A | YES ✔ |  | Business page
YouTube | youtube.com/@RationVeda | marketing@rationveda.com | Google account | YES ✔ |  | Brand channel
LinkedIn | linkedin.com/company/rationveda | nishtha@rationveda.com | Set in 1Password | Optional |  | Company page
X (Twitter) | x.com/RationVeda | marketing@rationveda.com | Set in 1Password | Optional |  | Lower priority
Pinterest | pinterest.com/rationveda | marketing@rationveda.com | Set in 1Password | Optional |  | Lower priority
Linktree | linktr.ee/rationveda | marketing@rationveda.com | Set in 1Password | Optional |  | Link in bio tool
Website & Commerce
Shopify Admin | rationveda.myshopify.com/admin | nishtha@rationveda.com | Set in 1Password | YES ✔ |  | Store admin
Google Analytics | analytics.google.com | marketing@rationveda.com | Google account | YES ✔ |  | Property: Ration Veda
Google Search Console | search.google.com/search-console | marketing@rationveda.com | Google account | YES ✔ |  | Site: rationveda.com
Meta Business Suite | business.facebook.com | Personal FB login | N/A | YES ✔ |  | Pixel, ads, commerce
Operations
WhatsApp Business / Interakt | app.interakt.ai |  | Set in 1Password | YES ✔ |  | Order management & broadcasts
ShipRocket | app.shiprocket.in |  | Set in 1Password | Optional |  | Shipping & logistics
Canva | canva.com | marketing@rationveda.com | Set in 1Password | Optional |  | Design tool
1Password / Bitwarden | 1password.com / bitwarden.com | nishtha@rationveda.com | MASTER PASSWORD | YES ✔ | personal email | Password manager — protect this!

## Timeline View
RATION VEDA — Setup Timeline (4-Week Sprint)
Day / Week | Category | Key Tasks | Deliverable | Owner | Done?
WEEK 1: Foundation
Day 1 | Security | Set up password manager (1Password/Bitwarden) | Password vault created | Founder
Day 1 | Domain | Verify domain, set up Cloudflare DNS | DNS configured, SSL active | Dev
Day 1-2 | Email | Set up Google Workspace, create all email accounts | 6 email addresses live | Founder
Day 2 | Email | Configure MX, SPF, DKIM, DMARC records | Email deliverability secured | Dev
Day 2-3 | Security | Enable 2FA on all accounts | All critical accounts secured | Founder
Day 3 | Social | Create Instagram Business Account + optimize profile | IG profile live | Marketing
Day 3 | Social | Set up Facebook Business Page | FB page live | Marketing
Day 3-4 | Operations | Update WhatsApp Business catalog & templates | WhatsApp catalog ready | Operations
Day 4 | Social | Create YouTube channel + LinkedIn page | YT & LI profiles live | Marketing
Day 4-5 | Content | Design Instagram Highlights + brand templates | 7 highlight covers + 4 templates | Marketing
Day 5 | Social | Create Google Business Profile | GBP live with photos | Marketing
WEEK 2: Website Build
Day 5-6 | Website | Purchase Shopify, connect domain | rationveda.com on Shopify | Dev
Day 6-7 | Website | Select theme, customize design | Brand-matched theme live | Dev
Day 4-7 | Content | Product photography session | 100+ product/lifestyle photos | Photographer
Day 7-10 | Website | Build all pages (Home, About, Process, Products, Contact) | Complete website structure | Dev + Content
Day 8-12 | Website | Add all products to catalog | Product pages live | Marketing
Day 10-12 | Website | Set up WhatsApp order redirect | Order flow working | Dev
WEEK 3: Technical & Content
Day 12-13 | Website | Set up Google Analytics + Search Console | Analytics tracking live | Dev
Day 12-13 | Website | Install Meta Pixel | Pixel tracking active | Dev
Day 13-14 | Website | SEO setup (titles, meta, schema) | SEO foundations set | Dev
Week 2-3 | Website | Install essential Shopify apps | Apps configured | Dev
Week 2 | Website | Enable PWA for mobile app-like experience | PWA active | Dev
Week 2 | Social | Set up Instagram Shopping + LinkedIn page | Shopping tags enabled | Marketing
Week 2 | Social | Register on X and Pinterest | Profiles created | Marketing
WEEK 4: Content & Launch
Week 3-4 | Content | Write brand copy document | Master copy doc ready | Copywriter
Week 1-4 | Content | Execute Instagram content plan (30-day plan) | 20+ posts published | Marketing
Week 4 | Content | Plan YouTube content pillars, shoot first video | First YT video uploaded | Marketing
Week 4 | Review | Test all flows: website, WhatsApp, social links | All systems verified | Founder
Week 4 | Launch | Announce to existing 702 customers via WhatsApp broadcast | Launch broadcast sent | Operations

## Cost Estimate
RATION VEDA — Digital Setup Cost Estimate
Item | Monthly Cost (₹) | Annual Cost (₹) | One-Time Cost (₹) | Notes
Essential (Must Have)
Domain renewal (rationveda.com) |  | 1200 |  | Annual renewal
Cloudflare (Free plan) | 0 | 0 |  | Free SSL, CDN, DNS
Google Workspace (1 user) | 136 | 1632 |  | Add ₹136/month per additional user
Shopify Basic Plan | 2000 | 24000 |  | Can start with trial
WhatsApp Business API (Interakt) | 999 | 11988 |  | Already using
Product Photography |  |  | 10000 | One-time professional shoot
Recommended
Canva Pro | 291 | 3500 |  | Annual plan is cheaper
Linktree Pro | 0 | 0 |  | Free plan sufficient
Email marketing (Mailchimp) | 0 | 0 |  | Free up to 500 contacts
Shopify Apps (reviews, SEO, WhatsApp) | 500 | 6000 |  | Estimate for essential apps
Ring light + tripod + lapel mic |  |  | 3000 | One-time for content creation
Optional / Later
Instagram/Facebook Ads (when ready) | 5000 | 60000 |  | Start small, scale with data
Influencer seeding | 5000 | 60000 |  | Barter + small fees initially
Shopify Mobile App Builder (Shopney) | 5000 | 60000 |  | Only at 5000+ customers
Custom App Development |  |  | 500000 | Only at 10000+ customers
TOTALS (Essential + Recommended)
Total Monthly (Essential) | 3635 |  |  | ₹3,635/month to run everything
Total One-Time Setup |  |  | 13000 | ₹13,000 one-time
Total Year 1 Cost (Essential + Recommended) |  | 61320 |  | ~₹61,000 for the full year